✅ Step 1 — Inventory (1–2 Days)

Create a master sheet with:

- Repository name

- Technology (Java, .NET, Node…)

- Pipeline exists? (Y/N)

- Sonar integrated? (Y/N)

- Last build date

- Last deployment environment

From:

- Bitbucket → list all repos

- Jenkins → list all jobs

- SonarQube → list all projects

👉 Goal: Identify gaps (repos without pipeline / sonar).

#########################################################################

✅ Implementation Plan – DevSecOps Governance Enablement

Scope:

- 0 Critical vulnerabilities promoted

- 100% secrets secured

- ≥98% naming convention compliance

- Full traceability (Bitbucket → Pipeline → Deployment)

- Controlled environment promotion (SIT → UAT → Pre-Prod → Prod)

1️⃣ Phase 1 – Assessment & Design (Week 1–2)

Objectives

- Baseline current pipeline maturity

- Identify gaps in:

  - SonarQube coverage

  - Secret handling

  - Naming conventions

  - Promotion controls

  - Traceability

Activities

- Inventory all repositories (per LOB / technology)

- Map current CI/CD pipelines

- Identify projects not integrated with SonarQube

- Review current Quality Gates

- Assess vault usage (Jenkins credentials / Azure Vault / HashiCorp Vault)

- Review naming standards documentation

Deliverables

- Gap Assessment Report

- Standardized Governance Framework

- Approved Target Architecture

Dependencies

- Access to:

  - SonarQube admin

  - Bitbucket admin

  - CI/CD tool admin

  - Deployment tools

- Input from Dev Leads per LOB

2️⃣ Phase 2 – Pilot Implementation (Week 3–5)

Target: 1–2 applications (different technologies if possible)

A. SonarQube Integration

Actions

- Integrate all branches with SonarQube

- Enforce:

  - No Critical / Blocker vulnerabilities

  - Coverage threshold (e.g., ≥80%)

  - No new security hotspots unresolved

- Configure:

  - Branch analysis

  - Pull Request decoration

  - Quality Gate blocking

Outcome

🚫 Pipeline fails automatically if:

- Critical vulnerabilities exist

- Quality Gate fails

B. Secrets Governance

Actions

- Remove hardcoded secrets

- Enforce:

  - Vault usage only

  - Pipeline variable encryption

- Enable secret scanning (e.g., Bitbucket scanning / Gitleaks)

KPI Target

✔ 100% secrets stored in vault
✔ 0 hardcoded credentials

C. Naming Convention Enforcement

Implementation

- Add pipeline validation script:

  - Build name format

  - Artifact naming format

  - Tag naming format

  - Branch naming standard

- Fail pipeline if non-compliant

KPI Target

≥98% compliance

D. Environment Promotion Gates

Model

SIT → UAT → Pre-Prod → Prod

Each stage requires:

- Quality Gate pass

- Manual approval (for higher environments)

- Security validation

- Change ticket reference

Controls

- Prevent direct Prod deployment

- Artifact immutability enforcement

- Version promotion only (no rebuild in higher env)

E. Full Traceability Implementation

Trace chain:

Bitbucket Commit ID
     ↓
Pipeline Build Number
     ↓
Artifact Version
     ↓
Deployment ID
     ↓
Environment

Implementation

- Inject Git commit hash into build

- Tag Docker images with:

  - Build number

  - Commit ID

- Store deployment metadata in log store or DB

- Enable dashboard reporting

3️⃣ Phase 3 – Rollout per LOB / Technology (Week 6–12)

Approach

Gradual rollout by:

- Line of Business

- Technology stack

- Application criticality

Example Timeline

| Week | Activity |
| --- | --- |
| 6–7 | LOB 1 – Java Applications |
| 8–9 | LOB 2 – .NET Applications |
| 10 | LOB 3 – Frontend / Node |
| 11 | Microservices / Containerized apps |
| 12 | Legacy applications |

4️⃣ Phase 4 – Governance Dashboard & Reporting (Week 10–12)

Management Dashboard Includes:

- % Applications Integrated with Sonar

- Critical Vulnerabilities Count

- Coverage % Trend

- Naming Compliance %

- Promotion Violations

- Traceability Audit Report

Weekly Automated Report

- Sent to:

  - ITQMS

  - Dev Managers

  - Security

- Includes:

  - Failing projects

  - Violations

  - Improvement trends

🎯 Target Completion Timeline

| Phase | Duration | Completion |
| --- | --- | --- |
| Assessment | 2 Weeks | Week 2 |
| Pilot | 3 Weeks | Week 5 |
| Rollout | 6–7 Weeks | Week 12 |
| Dashboard & Governance | Parallel | Week 12 |

Total Estimated Duration: 10–12 Weeks

🔒 Enforcement Summary

| Control | Enforcement Type |
| --- | --- |
| Critical Vulnerabilities | Automatic Pipeline Block |
| Secrets | Vault-only Policy |
| Naming | Pipeline Validation Script |
| Promotion | Manual Approval + Quality Gate |
| Traceability | Metadata Injection |

📌 Support Required

From ITQMS

- Policy approval

- Naming standard finalization

- Promotion approval workflow alignment

From Development Teams

- Fix legacy critical vulnerabilities

- Adopt naming standards

- Remove hardcoded secrets

From Infrastructure

- Vault configuration

- SonarQube capacity review

- CI/CD scalability check

📊 Risk Considerations

- Legacy code may initially fail Quality Gates

- Cultural resistance to blocking builds

- Increased pipeline execution time

- Resource bandwidth during rollout

Mitigation:

- Gradual enforcement (warning → block mode)

- Training sessions

- Executive sponsorship

🚀 Final Outcome

At project completion:

✔ 0 Critical vulnerabilities promoted
✔ 100% secret governance
✔ ≥98% naming compliance
✔ Full deployment traceability
✔ Controlled promotion gates
✔ Executive dashboard visibility

#####################################################################################

Perfect — here is the clean executive summary per part (what is required from DevOps).

✅ PART 1 – Scope + SonarQube Enforcement

1️⃣ Scope

Must apply to:

Technologies

- PL/SQL

- IBM webMethods

- Java

- React JS

- Node JS

LOBs

All listed LOBs (DXP → ERP-HR)

Environments

Dev → SIT → UAT → Pre-Prod → Prod

👉 No exclusions.

2️⃣ SonarQube Integration & Quality Gate

Using:
SonarQube

DevOps must ensure:

Coverage

- 100% repositories integrated

Quality Gate (New Code)

- No Blocker/Critical Bugs

- No Blocker/Critical Vulnerabilities

- All Hotspots reviewed

- Coverage ≥ 40% initially (configurable to 70%)

- Duplication < 3–5%

- No new Critical Code Smells

Security Controls

- SAST on every PR

- SCA (dependency scanning)

- Secrets detection

- Pipeline fails on Critical vulnerability

- Security checks before SIT/UAT/PreProd

✅ PART 2 – QMS Code Review Rules Enforcement

DevOps must:

- Configure Sonar Quality Profiles per technology

- Enable rule sets matching QMS checklist

- Enforce via Quality Gate

General Rules (All Tech)

- No commented code

- No TODO/FIXME in prod

- No empty catch / swallowed exceptions

- Exceptions logged or rethrown

- No hardcoded secrets

- No sensitive logs

- Complexity within threshold

- No dead code

Technology-Specific Rules

PL/SQL

- No SQL injection

- No empty WHEN OTHERS

- No SELECT *

- No excessive GRANT

IBM webMethods

- No hardcoded credentials

- Input validation

- Proper error handling

Java

- No injection (SQL/OS)

- No unsafe deserialization

- Try-with-resources

- Proper null handling

React

- No unsafe dangerouslySetInnerHTML

- Validate input

- Follow hooks rules

Node

- Sanitize inputs

- No blocking sync calls

- Handle all promises

- No unsafe child_process.exec

👉 Sonar must automatically detect violations.

✅ PART 3 – Naming Convention Enforcement

DevOps must enforce across:

- Release branches

- Tags

- Artifacts

- Deployments

Format:

R<Release>-<LOB>-v<Major.Minor.Patch>-<ENV>

Examples:

R05-DXP-v1.2.0-SIT

Pipelines must:

- Validate naming

- Reject non-compliant builds

Target:
≥98% compliance

✅ PART 4 – Deployment Gate + KPIs

Deployment Gate Enforcement

Before promotion to SIT/UAT/PreProd:

Must verify:

- Sonar Quality Gate = PASS

- SAST/SCA = PASS

- Secrets scan clean

- Required tests available

If any fails → block promotion.

KPI Targets

- 100% repos integrated

- Quality Gate Pass Rate ≥ 90% (start 40%)

- 0 Critical vulnerabilities promoted

- 100% secrets in vault

- ≥98% naming compliance

- Full traceability (Commit → Build → Deployment)

Using:
Bitbucket
Jenkins

✅ PART 5 – Required Actions from DevOps

DevOps must:

- Review all requirements

- Implement:

  - Sonar integration

  - QMS rule sets

  - Naming validation

  - Promotion gates

- Provide:

Implementation Plan including:

- Pilot phase

- Rollout per LOB/Tech

- Completion timeline

- Dependencies from:

  - ITQMS

  - Development teams

🎯 In One Clear Statement

DevOps is required to:

Establish strict DevSecOps governance across all repos and environments with automated enforcement, measurable KPIs, and blocked promotions for non-compliance.

Here is the practical way to start this project without getting overwhelmed.

✅ Step 1 – Get Alignment (Week 0)

Before touching Jenkins or Sonar:

Meet with:

- ITQMS (Ayman)

- Security

- Dev Leads (per major LOB)

Confirm:

- Starting thresholds:

  - Coverage = 40%

  - Gate pass target = 40% → then increase

- Enforcement mode:

  - Month 1 = Warning

  - Month 2 = Soft block

  - Month 3 = Hard block

- Pilot LOB selection (choose 1 Java + 1 Node app)

👉 Do NOT start with all LOBs.

✅ Step 2 – Baseline Assessment (Week 1)

Using:
Bitbucket
Jenkins
SonarQube

Create a sheet:

- Repo name

- Tech

- Sonar integrated?

- Gate status?

- Critical vulnerabilities?

- Naming compliant?

- Prod approval exists?

Output:
Current compliance % vs target.

✅ Step 3 – Build the Standard Model (Week 2)

Create one reference pipeline template:

Include:

- Sonar scan

- waitForQualityGate (fail if not pass)

- SAST

- SCA

- Secret scan

- Naming validation

- Approval gate before Prod

This becomes your golden template.

Do NOT modify all pipelines manually.
Create reusable shared library / template.

✅ Step 4 – Configure SonarQube Properly (Week 2–3)

Inside Sonar:

- Create Quality Profiles per tech

- Enable QMS rules

- Create one unified Quality Gate:

  - No Critical

  - Coverage ≥ 40%

  - Duplication < 5%

Test on pilot apps.

✅ Step 5 – Pilot Rollout (Week 3–5)

Pick:

- 1 Java app

- 1 Node/React app

Implement:

- Full Sonar enforcement

- Naming validation

- Promotion blocking

Measure:

- % build failures

- Dev friction

- Fix effort

Adjust thresholds if needed.

✅ Step 6 – Gradual Rollout (Week 6–12)

Roll out per LOB:

Week 6–7 → Java LOBs
Week 8–9 → Node/React
Week 10 → PL/SQL
Week 11 → webMethods
Week 12 → Legacy / remaining